# Project Progress Tracking Form

IS52018C Software Projects 201920

|  |  |
| --- | --- |
| **Project Name** | *Scale Shelves* |
| **Concept** | *A smart shelf with weight sensors that sends stock information to an app.* |
| **Project Number** | *24* |
| **Document Start Date** | *Week 6 of Term 1* |
| **Business Plan Objective** | *Increase the efficiency of inventory management, reducing time spent on it and occurrences of items being out of stock.* |
| **Sponsor/Supervisor** | *Frederic Fol Leymarie* |
| **Project Manager** | *Jasper Robinson* |
| **Gitlab space** | <https://gitlab.doc.gold.ac.uk/softproj24/smart-inventory-shelves> |

|  |  |  |
| --- | --- | --- |
| **Budget/hrs** |  | |
| Resource Name (Student Name) | | Budget/hrs |
| *Francis Aquino* | | *232 hrs* |
| *Jignesh Devji* | | *232 hrs* |
| *Marisa Doyne* | | *232 hrs* |
| *Christopher Mayes (Chris)* | | *232 hrs* |
| *Elhassania Ghazoini (Ania)* | | *232 hrs* |
| *Jasper Robinson* | | *232 hrs* |

**Objective/Scope**

* *Phase 1: Identifying the concept: Come up with ideas, discuss, decide, perform market research, refine the concept.*
* *Phase 2: Defining the concept. Continued stakeholder interaction to refine requirements, creating lists of scenarios and modelling those scenarios (UML).*
* *Phase 3: Prototyping the concept: Research, development of lo-fi prototype, development of hi-fi functional prototype, development of technical prototype, testing.*

**Milestone Plan and Revision Plan**

|  |  |  |  |
| --- | --- | --- | --- |
| Milestone ID | Revision Plan, including budget revision | Milestone Date | Resources Required |
| *1 Concept proposal* | *No change* | *11/10/19* | *All 2-3 Hrs* |
| 2 Requirements and Market study | No change, more extensive market research and interviews being to continue after. | 18/10/19 | All 2-3 Hrs |
| 3 Concept Design Model | No change, Models will be refined and improved before the final report. | 25/10/19 | All 3-4 hrs |
| 4 Prototype activity report | No change | 22/11/19 | All 14-28 hrs (total 4 weeks) |
|  |  |  |  |
|  |  |  |  |
| *Milestone n* | *Record reasons for changes to the milestone plans* | *Date for the milestone to be delivered. Cross through and replace with new date if the plan changes.* | *Resources that you will need to commit to achieve this milestone.*  *Student 1: x hrs*  *:*  *Student n: y hrs*  *Cross through and enter new resource commitment details if the plan changes.* |

**Status/Progress**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date** | Task ID | Progress & Status | Resources Used: Name & hrs |
| *11/10/19* | *M1 Concept proposal* | *M1 submitted. Decided on a project.* | *Francis - 0*  *Jignesh - 2*  *Marisa – 2.5*  *Christopher – 2.5*  *Elhassania – 2.5*  *Jasper - 2* |
| *18/10/19* | M2 Requirements and Market study | M2 submitted, refined project focus, interviews and market research for changed focus ongoing. | Francis – 3  Jignesh – 4  Marisa – 1.5  Christopher – 2.5  Elhassania – 2.5  Jasper – 2.5 |
| *25/10/19* | M3 Concept Design Model | M3 submitted, Models made for key areas of the app. These models may be expanded in the future | Francis – 2.5  Jignesh – 5  Marisa – 3.5  Christopher - 6  Elhassania – 7  Jasper – 10 |
| *3/11/19* | M4 Prototype activity report | Preliminary Prototype research done. Some lo-fi diagrams made. Waiting on members reports on research and specifics of what’s achievable for our prototype. | Francis - 2  Jignesh - 0  Marisa – 4.5  Christopher - 4  Elhassania – 6  Jasper – 7.5 |
| *10/11/19* | M4 Prototype activity report | Lo-fi prototype mostly done, List of specifications for Hi-fi prototypes generated. | Francis - 2  Jignesh - 0  Marisa – 8.5  Christopher - 0  Elhassania - 5  Jasper – 7 |
| *14/11/19* | M4 Prototype activity report | Progress on making Hi-fi prototype ready for stakeholder testing next week. | Francis – 2.5  Jignesh - 0  Marisa – 0  Christopher - 4  Elhassania – 5  Jasper – 5 |
|  | *A specific task leading to an outcome/milestone The Task ID should point to the associated Milestone ID* | *What progress has been made on the task and therefore what is the status of that task and the associated outcome/milestone. This usually expressed as a percentage of completion. Does the Milestone plan need to change?* | *Student 1: x hrs*  *:*  *Student n: y hrs* |

|  |  |  |  |
| --- | --- | --- | --- |
| **Cumulative Resource Usage/hrs** | | | |
| Revision Date | Resource Name | hrs Used | hrs Remaining |
| *30/9/19* | *Francis Aquino* |  | *232* |
| *11/10/19* | *Nothing reported* |  |  |
| *18/10/19* | *Market Research* | *3* | *229* |
| *25/10/19* | *- UML research*  *- Writing Scenarios/sequence notes*  *- Attending Interviews* | *0.5*  *1*  *1* | *226.5* |
| *3/11/19* | *- Prototyping research* | *1* | *225.5* |
| *10/11/19* | *-* Creating Use Cases/Scenarios/Sequence Lists | *2* | *223.5* |
| *14/11/19* | - LoFi Sketch and Storyboards  *-* HiFi Sketches & Prototypes | *2*  *0.5* | *221* |
| *27/4/19* | *Francis Aquino* | *z1 (26 weeks) hrs* | *232 - a1 - b1 … - z1 = 0 hrs* |
| *30/9/19* | *Jignesh Devji* |  | *232* |
| *11/10/19* | *- Thinking up ideas* | *2* | *230* |
| *18/10/19* | *- Market research* | *4* | *226* |
| *25/10/19* | - Stakeholder’s research/writing  - Attending Interviews  - Writing up interview notes | 2  2  1 | 221 |
| *3/11/19* | Nothing reported |  | 221 |
| *10/11/19* | Nothing reported |  | 221 |
| *14/11/19* | Nothing reported yet |  | *221* |
| *27/4/19* | *Jignesh Devji* | *z2 (26 weeks) hrs* | *232 – a2 – b2 … - z2 = 0 hrs* |
| *30/9/19* | *Marisa Doyne* |  | *232* |
| *11/10/19* | *-Group communication & Admin*  *- Thinking up ideas* | *0.5*  *2* | *229.5* |
| *18/10/19* | *-Group communication & Admin*  *- Market research* | 0.5  1 | 228 |
| *25/10/19* | *- Group communication & Admin*  *- UML research*  - Attending Interviews  - Writing up interview notes | *1*  *0.5*  *1*  *1* | 224.5 |
| *3/11/19* | *- Group communication & Admin*  - Prototyping - Storyboard  - Writing up interview notes | 0.5  2  2 | 220 |
| *10/11/19* | *- Group communication & Admin*  - Attending Interviews  - Writing up interview notes  - Creating Use Cases/Scenarios/Sequence Lists | 1  1  1.5  5 | 211.5 |
| *14/11/19* | *Nothing reported yet* |  |  |
| *27/4/19* | *Marisa Doyne* | *zn (26 weeks) hrs* | *232 – an – bn … - zn = 0 hrs* |
| *30/9/19* | *Christopher Mayes* |  | *232* |
| *11/10/19* | *- Thinking up ideas*  *- Writing up milestone* | *2*  *0.5* | *229.5* |
| *18/10/19* | *- Market research* | *2.5* | *227* |
| *25/10/19* | - Stakeholder’s research/writing  *- UML research*  *- Making UML diagrams*  *- Attending Interviews* | *1*  *3*  *1*  *1* | *221* |
| *3/11/19* | *- Prototyping research*  *- Prototyping storyboard* | *1*  *3* | *217* |
| *10/11/19* | *Nothing reported* |  |  |
| *14/11/19* | *-LoFi Sketch and Storyboards* | *4* | *213* |
| *27/4/19* | *Student n* | *zn (26 weeks) hrs* | *232 – an – bn … - zn = 0 hrs* |
| *30/9/19* | *Elhassania Ghazoini* |  | *232* |
| *11/10/19* | *- Thinking up ideas*  *- Writing up milestone* | *2*  *0.5* | *229.5* |
| *18/10/19* | *- Market research* | *2.5* | *227* |
| *25/10/19* | - Stakeholder’s research/writing  *- UML research*  *- Writing scenarios and sequence notes*  *- Making UML diagrams*  *- Attending Interviews*  *- Writing up interview notes* | *1*  *2*  *1.5*  *1*  *1*  *0.5* | *220* |
| *3/11/19* | *- Prototyping Research*  *- Prototyping Storyboard* | *4*  *2* | *214* |
| *10/11/19* | - Creating Use Cases/Scenarios/Sequence Lists | *5* | *209* |
| *14/11/19* | *-* breaking down tasks?  - Lo-fi sketch and Storyboards | *1*  *4* | *204* |
| *27/4/19* | *Elhassania Ghazoini* | *zn (26 weeks) hrs* | *232 – an – bn … - zn = 0 hrs* |
| *30/9/19* | *Jasper Robinson* |  | *232* |
| *11/10/19* | *- Thinking up ideas* | *2* | *230* |
| *18/10/19* | *- Market Research*  *- Writing up milestone* | *2*  *1* | *227* |
| *25/10/19* | *- Stakeholders research/writing*  *- Researching UML*  *- Writing scenarios and sequence notes*  *- Making UML diagrams*  *- Attending Interviews*  *- Writing up interview notes* | *1*  *2*  *1.5*  *3*  *2*  *0.5* | *217* |
| *3/11/19* | *- Creating Gitlab space, moving all documents to the wiki, organising the wik, linking pages and adding extra pages and information.*  *- Prototyping research*  *- Prototyping sketch* | *6*  *1*  *0.5* | *209.5* |
| *10/11/19* | - Group Administration/ wiki maintenance  *- Researching project management and GANNT charts*  *- Making a GANNT chart*  - Creating prototyping wiki page and breaking down tasks | *1*  *2*  *1*  *3* | *202.5* |
| *14/11/19* | *- Lo-fi Sketches/ mock-ups*  *- Hi-fi Sketches/ prototyping*  Group Communication & Administration | *1*  *1*  *3* | *197.5* |
| *27/4/19* | *Jasper Robinson* | *zn (26 weeks) hrs* | *232 – an – bn … - zn = 0 hrs* |